## Cover Sheet
ASSIGNMENT 1
DO INITIAL VERSION OF PERSONAL WBS
CSE 6329
Software Metrics and Quality Engineering
Spring, 2016
Name | Yerramsetti Sandeep
ID | 1001156902
Points
(/10) Correct Format, including name on top, totals, etc.
(/50) Reasonable list of tasks for each assignment
(/40) Reasonable estimates, actual and earned hours.
(100) Total Assignment Grade
Comments from Grader
1

## Instructions
Instructions for Weekly WBS Entries
Step 1 - Enter hours worked each week
At the end of each week, fill in hours worked on each task, as follows:
(hours may be entered in whole hours, such as 2, or in tenths of an hour, such as 1.3)
For each task:
If you did no work on that task, do nothing.
If you worked on that task during the past week:
Enter total hours worked on the task in the column corresponding to the current week (column U through AJ).
Cell should change color when you enter a non-zero value.
Enter total hours of work remaining on the task in column E:
If the task is complete, enter 0 hours remaining.
The total hours remaining is your best current estimate, which may differ from what was originally estimated.
Step 2: Check for errors
Review all totals and numbers and make sure everything seems correct.
Make corrections as necessary
Step 3: Record Etimated Hours Remaining at end of current week
Copy the "total estimated hours remaining" (bottom of column E) to estimated hours remaining cell for current week
Cell will change color
This will update the burndown and burnup charts
Step 4: Update Earned Value
Enter 0 in days earned this week row for the current week (near bottom)
For each task that has completed during the current week:
Find the originally estimated hours for that task and add it to the hours earned this week for the current week
When done, this will update the earned value and the earned value chart

## WBS
|  |  | PWBS | [9 empty] | Planned Effort | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 | 3.3688 |  | 53.9
Open |  | 2016 sp | CSE 6329-002 | Schedule | [8 empty] | Cumulative Plan (PV) | 3.3688 | 6.7375 | 10.1063 | 13.475 | 16.8438 | 20.2125 | 23.5812 | 26.95 | 30.3187 | 33.6875 | 37.0562 | 40.425 | 43.7937 | 47.1625 | 50.5312 | 53.9
In Progress |  | Yerramsetti Sandeep | [10 empty] | Estimated Effort Remaining | 53.9 | 50.5312 | 47.1625 | 43.7937 | 40.425 | 37.0562 | 33.6875 | 30.3187 | 26.95 | 23.5812 | 20.2125 | 16.8437 | 13.475 | 10.1062 | 6.7375 | 3.3687
Complete |  | Actual Results |  |  |  | Estimates |  | WBS | [5 empty] | Actual Hours Worked and Earned
Status |  | Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week |  | Estimated Hours of Effort | Planned Completion Week | Task # |  |  |  |  | Task Description Week Ending >> | 2016-01-22 | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-22 | 2016-04-29 | 2016-05-06 | insert new column here | Total Hours Worked
[8 empty] | 10000 | A1 - Develop PWBS
[8 empty] | 11000 |  | Read and Analyze A1 SOW for PWBS | [20 empty] | 0
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 11100 |  |  | List tasks to be performed |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 |  | 11200 |  |  | Estimate hours required for each task |  |  | 2016-01-22: 0.4 |  | 0.4
Complete |  | 0 | 1 | 0.4 | 0.4 | 0.4 |  | 11300 |  |  | Break into smaller sub-tasks as required |  |  | 2016-01-22: 0.4 |  | 0.4
Complete |  | 0 | 0.8 | 1.3 | 1.3 | 1.3 |  | 11400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  | 2016-01-22: 1.3 |  | 1.3
Complete |  | 0 | 0.4 | 0.4 | 0.4 | 0.4 |  | 11500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  | 2016-01-22: 0.4 |  | 0.4
[8 empty] | 12000 |  | Read and Analyze A2 SOW | [20 empty] | 0
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 12100 |  |  | List tasks to be performed |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 12200 |  |  | Estimate hours required for each task |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 1 | 1 | 1 | 1 |  | 12300 |  |  | Break into smaller sub-tasks as required | [19 empty] | 1 | bar: 2016-01-22
Complete |  | 0 | 0.8 | 0.5 | 0.5 | 0.5 |  | 12400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 12500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  | 2016-01-22: 0.5 |  | 0.5
[8 empty] | 13000 |  | Read and Analyze A3 SOW | [20 empty] | 0
Complete |  | 0 | 0.8 | 1 | 1 | 1 |  | 13100 |  |  | List tasks to be performed | [19 empty] | 1 | bar: 2016-01-22
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 13200 |  |  | Estimate hours required for each task |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.8 | 1 | 1 | 1 |  | 13300 |  |  | Break into smaller sub-tasks as required | [19 empty] | 1 | bar: 2016-01-22
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 13400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 13500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  | 2016-01-22: 0.5 |  | 0.5
[8 empty] | 14000 |  | Read and Analyze A4 SOW | [20 empty] | 0
Complete |  | 0 | 1 | 1 | 1 | 1 |  | 14100 |  |  | List tasks to be performed | [19 empty] | 1 | bar: 2016-01-22
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 14200 |  |  | Estimate hours required for each task |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 1 | 1 | 1 | 1 |  | 14300 |  |  | Break into smaller sub-tasks as required | [19 empty] | 1 | bar: 2016-01-22
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 14400 |  |  | Modify template to add tasks and correct formulas/coloring |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 14500 |  |  | Record estimated hours in Estimated Hours of Effort column |  |  | 2016-01-22: 0.5 |  | 0.5
Complete |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 15000 |  | Submit A1 (Draft) |  |  |  | 2016-01-22: 0.5 |  | 0.5
Open |  | 1 | 0 |  |  | 1 |  | 16000 |  | Review comments from TA/Instructor and Correct Mistakes | [20 empty] | 0
[8 empty] | 17000 |  | Make Weekly Updates to PWBS | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17100 |  |  | Updates for 9/11 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17200 |  |  | Updates for 9/18 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17300 |  |  | Updates for 9/25 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17400 |  |  | Updates for 10/9 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17500 |  |  | Updates for 10/16 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17600 |  |  | Updates for 10/23 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17700 |  |  | Updates for 10/30 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17800 |  |  | Updates for 11/6 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17900 |  |  | Updates for 11/13 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17910 |  |  | Updates for 11/20 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17920 |  |  | Updates for 11/27 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17930 |  |  | Updates for 12/4 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 17940 |  |  | Updates for 12/11 | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 18000 |  | Submit Final PWBS | [20 empty] | 0
[8 empty] | 20000 | A2 | [21 empty] | 0
[8 empty] | 21000 |  | Read and Analyse A2 SOW | [20 empty] | 0
Open | 1 | 1 | 0 | 1 | 1 | 1 |  | 21100 |  |  | learning recording and analysis tools | [19 empty] | 0
Open |  | 0.7 | 0 |  |  | 0.7 |  | 21200 |  |  | learning about product characteristics | [19 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 21300 |  |  | Analyze defect characteristics | [19 empty] | 0
Open |  | 0.3 | 0 |  |  | 0.3 |  | 21400 |  |  | learning data spreadsheet | [19 empty] | 0
[8 empty] | 22000 |  | Analyse post release quality | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 22100 |  |  | produce graph | [19 empty] | 0
[8 empty] | 23000 |  | analyse post release quality history | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 23100 |  |  | produce graphs | [19 empty] | 0
[8 empty] | 24000 |  | Measure correct quality | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 24100 |  |  | analyze total uncorrected defect | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 24200 |  |  | produce graph | [19 empty] | 0
Open |  | 1.2 | 0 |  |  | 1.2 |  | 25000 |  | Read about specific measures | [20 empty] | 0
Open |  | 1.2 | 0 |  |  | 1.2 |  | 27000 |  | Analyze measures and produce a graph with information | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 28000 |  | Documentation | [20 empty] | 0
[8 empty] | 30000 | A3 | [21 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 31000 |  | Read and analyse A3 SOW | [20 empty] | 0
[8 empty] | 32000 |  | devoploing program, producing flowgragh, determine cyclometric complexcity | [20 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 32100 |  |  | write a c program with the conditions mentioned | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 32200 |  |  | produce a flowgragh of the funciton | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 33300 |  |  | compute the cyclometric complexity of the funtion desinged | [19 empty] | 0
[8 empty] | 33000 |  | Review and evaluate the three programs | [20 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 33100 |  |  | review each program and note the errors | [19 empty] | 0
Open |  | 0.9 | 0 |  |  | 0.9 |  | 33200 |  |  | produce the flowgraph of each program | [19 empty] | 0
Open |  | 1.2 | 0 |  |  | 1.2 |  | 33300 |  |  | cyclomatic complexity of the program | [19 empty] | 0
Open |  | 0.7 | 0 |  |  | 0.7 |  | 34000 |  | re-check funtional requeirements | [20 empty] | 0
Open |  | 0.7 | 0 |  |  | 0.7 |  | 35000 |  | re-check non functional requirements | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 36000 |  | documentation | [20 empty] | 0
[8 empty] | 40000 | A4 | [21 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 41000 |  | Read and Analyse A4 SOW | [20 empty] | 0
[8 empty] | 42000 |  | produce swimlane diagram | [20 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 42100 |  |  | examine the handouts to identify all the organisations and about the process | [19 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 42200 |  |  | identify the order of the flow and the dependencies and design a control flow diagram | [19 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 42300 |  |  | produce and verify the swim lane diagram | [19 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 42400 |  |  | analyse the diagrams to check about the delays | [19 empty] | 0
[8 empty] | 43000 |  | produce a cause map | [20 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 43100 |  |  | analyse the problems that contribute to customers and produce a cause map | [19 empty] | 0
Open |  | 1 | 0 |  |  | 1 |  | 44000 |  | research about statistical analysis techniques | [20 empty] | 0
Open |  | 1.5 | 0 |  |  | 1.5 |  | 45000 |  | read about the techniques on root cause problems | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 46000 |  | Use the techniques to find the underlysing problems | [20 empty] | 0
Open |  | 0.5 | 0 |  |  | 0.5 |  | 47000 |  | documentation | [20 empty] | 0
Open |  | 4 | 0 |  |  | 4 |  | 50000 | E1 - Study for Midterm Exam | [21 empty] | 0
Open |  | 4 | 0 |  |  | 4 |  | 60000 | E2 - Study for Final Exam | [21 empty] | 0
Spare Task Rows - For use in Inserting New Tasks and Sub-Tasks
[8 empty] | 90000 | Spare Parent Task - Top Level | [21 empty] | 0
[8 empty] | 99000 |  | Spare Parent Task - Second Level | [20 empty] | 0
[8 empty] | 99900 |  |  | Spare Parent Task - Third Level | [19 empty] | 0
Open |  | 0 | 0 |  |  |  |  | 91000 |  | Spare Sub-Task - Second Level | [20 empty] | 0
Open |  | 0 | 0 |  |  |  |  | 99100 |  |  | Spare Sub-Task - Third Level | [19 empty] | 0
Open |  | 0 | 0 |  |  |  |  | 99910 |  |  |  | Spare Sub-Task - Fourth Level | [18 empty] | 0
Totals >> |  | 40.4 | 13.5 |  |  | 53.9 |  | Total Actual Hours Worked >> | [5 empty] | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ^ | ^ | ^ |  | ^ | ^ | Cumulative Actual Hours (AC) >> | [5 empty] | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 |  | 13.5
|  | Total Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week |  | Total Hours Originally Estimated | Planned Completion Week | Estimated Hours Remaining (copy each week from total in column E) >>
|  | (copy to the right at end of each week) | (should match cumulative actual Hours) | (fill in when the task is complete) |  | (should match cumulative planned effort) | [6 empty] | Week Number >> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Hours Earned This Week >>
[8 empty] | Cumulative Hours Earned (EV) >> | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0